## Purchase List
Description | Comment | Quantity | Distributer | Status
Periscope Brewster Angled D-Scan
Periscope + Translation HeNe |  |  |  | Design not started
Periscope Main Beam |  |  |  | ?
Ground Plate for CMs |  |  |  | ?
Holed Mirror Translation | Frederik | 1 |  | ?
Mount for 'Swiss Cheese' mirror | Aline | 1 |  | Design not started
Filter ( Lanex) | Find it or buy it! (Might be at Greque) | 1 |  | Found
TL Silver Mirror 3" |  | 4 | direct | ?
TL Silver Mirror 2" |  | 4 | direct | ?
TL Silver Mirror 1" |  | 4 | direct | ?
Mount 3" |  | Verify stock + check with Benoit for what has already been ordered | Newport
Femtolasers Silver Mirror 1.5" |  | 4 | BFI | Quotation requested 02/02/2015 FB
1.5" mirror mounts |  | 4 | ? | ?
Window Flange | For SH Wavefront Sensor : what coating? | Verify stock |  | Not ordered
Ceramic Plates | Beamblocking | 10 |  | Not ordered
Translation/flip for Beam block |  | 1 |  | Not designed
Pico Mount 3" | Compatible for our vacuum | 1 |  | Quotation requested 04/02/2015 FB
Pico Mount 1" | Compatible for our vacuum | 1 |  | Quotation requested 04/02/2015 FB
ISO-K Tee + 2 Flanges | ISO 160 - | 1 |  | Quote requested 28/01/2015
Vacuum-compatible subd 15 cable | 3 metres | 1 |  | Ordered on 29/01/2015
Shutter connector | Do we have everything? |  |  | Not done
Conformité ligne PI | Is the performance of the translation stage up to specs? |  |  | Not done
Add wedge to addtenuator design |  |  |  | in progress @Greg's